## Estimated
Estimated |  | Estimated Person-Months
|  | Analysis |  |  | Design |  |  |  |  | Development |  |  |  |  | Test Planning |  |  | Test Execution |  |  | ID | Location | Monthly Cost | Currency
ID | Task Name | BJ | ID | SE | BJ | ID | SE | KR | CZ | BJ | ID | SE | KR | CZ | BJ | ID | SE | BJ | ID | SE | BJ | Beijing | 25 | K RMB | Headoffice
1 | Safety | [19 empty] | ID | Indonesia | 15000 | K IDR
1.a. | Informational | [19 empty] | SE | Sweden | 45 | K SEK
1.a.i. | Proximity Sensors (Reverse, forward and gutter) | Analysis BJ: 1; Design BJ: 2.75; Development ID: 4.5; Test Planning BJ: 1.25; Test Execution ID: 3 | KR | Korea | 8000 | K KRW
1.a.ii. | Tyre Pressure Sensors | Analysis BJ: 1.5; Design BJ: 3.5; Development ID: 7; Test Planning BJ: 2.25; Test Execution ID: 2.75 | CZ | Czech Republic | 200 | K CZK | Subcontractor
1.a.iii. | Driver Fatigue Sensor | Analysis BJ: 2; Design BJ: 5.5; Development ID: 8.75; Test Planning BJ: 2.75; Test Execution ID: 5.75
1.a.iv. | Doors closed | Analysis BJ: 0.5; Design BJ: 1.25; Development ID: 2; Test Planning BJ: 0.75; Test Execution ID: 1.25 |  |  | K: 1000
1.b. | Control
1.b.i. | Locking System | Analysis SE: 0.5; Design SE: 1.5; Development CZ: 0.75; Test Planning SE: 0.75; Test Execution ID: 1.75
1.b.ii. | Wind-screen wipers | Analysis SE: 0.75; Design SE: 1.75; Development ID: 3.25; Test Planning SE: 1.25; Test Execution ID: 2.25
1.b.iii. | Lighting System | Analysis SE: 1.25; Design SE: 3.25; Development ID: 5.23; Test Planning SE: 1.5; Test Execution ID: 3.5
1.b.iv. | Engine | Analysis SE: 4.75; Design SE: 9.75; Development SE: 11; Test Planning SE: 6; Test Execution SE: 11.5
1.c. | Critical
1.c.i. | Ignition | Analysis SE: 2.25; Design KR: 3; Development BJ: 4.5; Test Planning SE: 3; Test Execution ID: 6
1.c.ii. | Power Steering | Analysis SE: 2.5; Design SE: 6.5; Development KR: 5; Test Planning SE: 4.5; Test Execution ID: 8
1.c.iii. | ABS | Analysis SE: 1.5; Design SE: 3.75; Test Planning SE: 2.25; Test Execution SE: 4.25
1.c.iv. | Electronic Stability Program (ESP) | Analysis BJ: 2; Design BJ: 4.75; Development BJ: 5; Test Planning BJ: 2.75; Test Execution SE: 5.25
1.c.v. | Airbags | Analysis BJ: 1.5; Design BJ: 4.25; Development BJ: 4.5; Development SE: 4; Test Planning BJ: 1.25; Test Execution BJ: 4.25
2 | Entertainment
2.a. | Radio | Analysis SE: 0.5; Design SE: 0.5; Development ID: 1; Test Planning SE: 0.5; Test Execution ID: 1.25
2.b. | CD | Analysis SE: 0.5; Design SE: 0.5; Development ID: 1.25; Test Planning SE: 0.5; Test Execution ID: 1.25
2.c. | Phone (Bluetooth) | Analysis BJ: 0.5; Design BJ: 0.5; Development ID: 2.75; Test Planning BJ: 0.5; Test Execution ID: 2
2.d. | iPod interface | Analysis BJ: 0.5; Design BJ: 0.75; Development ID: 3.25; Test Planning BJ: 0.5; Test Execution ID: 2.5
3 | Satellite Navigation
3.a. | Location | Analysis SE: 1.25; Design SE: 1.5; Development SE: 3.5; Test Planning SE: 1.25; Test Execution ID: 4.25
3.b. | Map Display | Analysis BJ: 3; Design BJ: 3.25; Development BJ: 7; Test Planning BJ: 2.25; Test Execution BJ: 9
3.c. | Direction Planning | Analysis BJ: 3; Design BJ: 4.25; Development ID: 17; Test Planning BJ: 2; Test Execution ID: 12
4 | Comfort
4.a. | Power locking | Analysis SE: 0.5; Design KR: 0.25; Development SE: 1; Test Planning SE: 0.5; Test Execution SE: 1.25
4.b. | Windows | Analysis SE: 0.5; Design KR: 0.25; Development ID: 1; Test Planning SE: 0.5; Test Execution ID: 1.5
4.c. | Placement of seat and steering wheel tailored for each registered driver. | Analysis BJ: 1.5; Design BJ: 2; Development ID: 7.25; Test Planning BJ: 1.25; Test Execution ID: 6.5
| Total Person Months | 17 | 0 | 16.75 | 32.75 | 0 | 29 | 3.5 | 0 | 21 | 64.23 | 19.5 | 5 | 0.75 | 17.5 | 0 | 22.5 | 13.25 | 65.5 | 22.25
| Number of Persons | 6 | 0 | 12 | 12 | 0 | 20 | 12 | 0 | 8 | 12 | 12 | 20 | 6 | 8 | 0 | 12 | 12 | 12 | 16
| Max Person Months excl. Project Management | 18 |  | 36 | 36 |  | 60 | 36 |  | 48 |  | 72 | 120 |  | 24 |  | 36 | 72 |  | 96